## Overview
Sample Migration Checklist from Cognos Business Intelligence to IBM Cognos Analytics on Cloud Hosted/Dedicated
Not all steps will apply to you. You should tailor the checklists and process for your own situation.
A typical process looks like this:
And the typical high level steps look like this:

## Assess Checklist
Sample Activity Checklist - For Illustration Purposes Only - Your upgrade may need more or less activities
Version xx.x on-premise to IBM CA ON CLOUD DEDICATED Version 11.1.X
ASSESS: | DISCOVER -> EVALUATE -> PLAN -> PREPARE
STAGE | TASK | OWNER | COMPLETED Y/N | NOTES
Discover | Review Supported Environments to ensure compatability with proposed infrastructure earmarked for upgraded environment |  |  | https://www.ibm.com/software/reports/compatibility/clarity/index.html
Discover | Check documentation for new features, fixes, or deprecated features |  |  | https://www.ibm.com/support/knowledgecenter/SSEP7J_11.1.0/com.ibm.swg.ba.cognos.cbi.doc/welcome.html
Discover | Investigate online FAQs and configuration actions |  |  | https://www.ibm.com/support/knowledgecenter/SSEP7J_11.1.0/com.ibm.swg.ba.cognos.inst_cr_winux.doc/c_inst_crit_config.html https://community.ibm.com/community/user/businessanalytics/home
Discover | Stand up CA in a sandbox |  |  | Get a feeling for changes to end user workflow whilst reviewing steps required for installation and migration of content.
Evaluate | Impact to users (new UI, changes to bookmarks, changes to user workflow) |  |  | Understand what education may needed for user adoption, note with roles (end user, author, modeller, etc) https://www.ibm.com/communities/analytics/cognos-analytics-blog/library-of-videos-for-ibm-cognos-analytics/
Evaluate | Review SaaS entitlements to ensure all your users / usage types are covered
Evaluate | Gather Inventory and Identify content to be upgraded |  |  | Use cognos audit reports to determine last time reports were run, ask users if they still need the reports; it's a good time to do housecleaning
Evaluate | Run Consistency Check against Content store to clean up any user IDs assigned to content that are no longer applicable |  |  | Use consistency check to verify referential integrity of content store
Evaluate | Identify reports using CQM queries; you will need to convert these to DQM queries before migrating content to the SaaS environment |  |  | Legacy CQM queries are not supported in the SaaS offering
Evaluate | Review any SDK or customizations to ensure they're compatible with the SaaS offering |  |  | Most things are supported but some are not; if you have customizations, check on these thoroughly
Evaluate | Identify data source(s) and their IP addresses; you will need these later for configuration in the SaaS offering |  |  | The SaaS offerings typically require IP addresses; using names is not supported
Evaluate | If you use trigger scripts to kick off jobs and if these were written for Windows, review updates needed to work on cloud |  |  | If triggers are not used or non-windows today, then they should still work
Evaluate | Determine if S3 / cloud object storage is needed and get budget/approvals to purchase this (used for save/burst to file system) |  |  | If you save to an external file system today, you will need to convert to an approved S3 vendor. Note: If you cannot use cloud, there are options like MinIO that allow your on-premise file system to appear as S3 to Cognos.
Evaluate | Decide on tools needed for upgrade (MotioCI and MotioPI or BSP MetaManager recommended) |  |  | Consider tools to help with inventory review, validation testing, mass remediation efforts, and version control
Evaluate | Determine who in the company will need to work on the upgrade |  |  | Will the user community take ownership of business area reports? Identify key personel who have areas of responsibility
Evaluate | Develop timeline for upgrade project |  |  | Review dates for withdrawl of software support, use in conjunction with the enterprise mandate to determine timeline for upgrade
Plan | Create SaaS migration project plan (include content upgrade tasks, DQM conversion tasks, uploading to the SaaS instance tasks) |  |  | Don't forget the DQM conversion step - This is important to plan to do on-premise before migrating to cloud
Plan | Create SaaS onboarding plan (where you work with SaaS Administrators to setup for SaaS environment)
Plan | Create content validation plan (compare content in old environment to new environment) |  |  | Will you have test scripts? Who will create them? Who will be responsible for validating report output or use of automation testing
Plan | Create Content deployment plan |  |  | How will content be upgraded? Which content will be deployed? How will it be promoted? Will you move all content at once?
Plan | Create plan for continual development , such as code freeze or handling changes during migration period |  |  | Some companies freeze new report/dashboard development during migration weeks. Others allow users to generate content. If the latter, remember to redeploy all changes before go live.
Plan | Cutover date planning |  |  | What will happen on cutover date. Consider DNS changes for links that end users have saved, time required to migrate and upgrade report specs, rollback contingencies, data movement, 3rd party or companion applications and schedules
Plan | Rollout to end users |  |  | Plan the rollout to end users, all users at once or partial rollout to determine success prior to rolling out to all users?
Plan | New Feature enablement |  |  | Identify users with business case for use of new features. Plan training and new feature enablement when upgraded software is available
Prepare | Order and set up S3 buckets if saving Cognos content to external storage (eg. If you use features: save to file, burst to file, etc…) |  |  | You will likely perform your upgrade tasks on-premise and prepare your content before uploading to the SaaS instance.
Prepare | Servers available and ready for cognos installation to create an upgrade sandbox (if needed) |  |  | You will likely perform your upgrade tasks on-premise and prepare your content before uploading to the SaaS instance.
Prepare | Operating System patched and prepped for cognos installation (if sandbox is needed) |  |  | Installation of the supported operating system, including any specific path requirements as noted in the planning stage along with third party software such as database drivers and runtime environment
Prepare | Content Repositories created (databases for content store, notification, audit, etc…) (if sandbox is needed) |  |  | Create databases to host Content Store, Notification Store, Mobile Store, Audit Store, Human Task store as required. Ensure authentication mechanism is set as required by the application and plan
Prepare | Write test scripts or checklists for validation stage that testers will follow |  |  | In some cases requiring stringent test requirements, writing test scripts helps the QA tester remember to test certain features and numbers
Prepare | Create a temporary "upgrade guild" or "upgrade center or excellence" for communication of the upgrade progress and rollout information |  |  | Consider forming a mechanism for sharing knowledge and communicate updates throughout the upgrade process
Prepare | Prepare staff for upcoming activities and responsibilities |  |  | Ensure identified resources are ready to execute; set expectations with user community of the upcoming upgrade activities
Approve Planning & Preparations as complete

## SaaS Onboarding Checklist
Sample Activity Checklist - For Illustration Purposes Only - Your upgrade may need more or less activities
Version xx.x on-premise to IBM CA ON CLOUD DEDICATED Version 11.1.X
ONBOARD TO SAAS OFFERING |  | PROVISION -> PREPARE CONTENT -> WELCOME KIT -> CONFIGURE -> TAILOR
STAGE | ENVIRONMENT | TASK | WHO | COMPLETED Y/N | EST START DATE | EST END DATE | DURATION | ACTUAL START DATE | ACTUAL END DATE | NOTES
Order | SAAS | Ensure technical contact, chosen data center location, and URL name are submitted correctly on order
Provision* | SAAS | *IBM will provision the environment for you. You just wait during this time.
Prepare Content | Upgrade Sandbox | While you work through the checklist on this page, prepare your content for uploading to SaaS by performing these steps | [7 empty] | you will want to do this on-premise while waiting for your SaaS instance to be setup completely. Also, if you attempt to go from C10 to SaaS directly, you will likely run into issues which will make it more difficult to remediate. It is typically smoother when done on-premise first.
Prepare Content | Upgrade Sandbox | Install an upgrade sandbox on-premise to prepare your content (see Install checklist)
Prepare Content | Upgrade Sandbox | Upgrade your content and convert your CQM based content to DQM (See upgrade checklist)
Prepare Content | Upgrade Sandbox | Test/remediate your SaaS-ready content
Welcome | SAAS | Receive and read welcome kit from IBM once initial SaaS instance is ready w/login and instructions
Welcome | SAAS | Log in and test your connectivity; note the new URL and ensure it is correct
Configure | SAAS | Follow instructions in the welcome kit which will include the below items
Configure | SAAS | Completing the VPN form and submitting via support ticket
Configure | SAAS | Scheduling a call w/your network admin and IBM network admin to setup and test the VPN
Configure | SAAS | Completing forms for datasource driver configurations, authentication configurations, etc
Configure | SAAS | Working with support to ensure SFTP works
Configure | SAAS | Request latest version of FM and/or Transformer download files from support (if you don't already have them) | [7 empty] | *You must use the correct version of these tools. Older versions may not connect due to SHA security changes.
Configure | SAAS | Test SaaS instance and resolve any issues (test emailing a report, test scheduling, poke around)
Configure | Developer laptop or local server | Install & configure & test FM connection to SaaS instance
Configure | Developer laptop or local server | Install & configure & test Transformer connection to SaaS instance (if using Transformer)
Configure | Developer laptop or local server | Install & configure & test tools like MotioCI / MotioPI / Techdaa BSP Metamanager, etc (if using)
Tailor | SAAS | Work with support on intial load of your content store to deploy groups/roles
Tailor | SAAS | Apply custom themes / extensions / templates; you may choose to create new as these are new concepts in CA11 if you are coming from Cognos 10.x
Tailor | SAAS | Upload content after it's been prepared on-premise and made SaaS-ready (upgraded/DQM converted, etc) (see Upgrade checklist)
Repeat | SAAS | If your SaaS order includes both a Dev and Prod SaaS instance, repeat above steps as required
Approve SaaS Instance

## Migration Checklist
Sample Activity Checklist - For Illustration Purposes Only - Your upgrade may need more or less activities
Version xx.x on-premise to IBM CA ON CLOUD DEDICATED Version 11.1.X
GO LIVE: |  | UNIT TEST -> PARALLEL TEST -> ENABLE -> CUTOVER -> GO LIVE
STAGE | ENVIRONMENT | TASK | WHO | COMPLETED Y/N | EST START DATE | EST END DATE | DURATION | ACTUAL START DATE | ACTUAL END DATE | Notes
Unit Test | SaaS Dev* | Upload prepared and accepted content to your SaaS instance (if content not saas-ready yet, see Install and Upgrade tabs) | [7 empty] | *if your SaaS order did not include SaaS Dev, then do this in SaaS Prod
Unit Test | SaaS Dev* | Unit test content after uploaded to SaaS | [7 empty] | *if your SaaS order did not include SaaS Dev, then do this in SaaS Prod
Unit Test | SaaS Dev* | Have users or UAT team test content and approve | [7 empty] | *if your SaaS order did not include SaaS Dev, then do this in SaaS Prod
Unit Test | SaaS Dev* | Remediate issues that arise and repeat testing until fully accepted | [7 empty] | *if your SaaS order did not include SaaS Dev, then do this in SaaS Prod
Parallel | SAAS PROD | Upload approved content from SaaS Dev to SaaS Prod
Parallel | SAAS PROD | If any internal systems point to the CA URL, then you will need to update the URL to the new SaaS instance
Parallel | SAAS PROD | Identify target group for use of new production environments (one group at a time or all at once)
Parallel | SAAS PROD | Remember to copy audit database history to the new audit database (if you are using audit)
Parallel | SAAS PROD | Redeploy any changes that occurred in the old environment during the testing/parallel period (ignore if code freeze was implemented)
Parallel | SAAS PROD | Have users actively use the new SaaS instance instead of their old environment, turning on schedules in new as well | [7 empty] | Roll out to selected groups, or to all users per project plan
Enable | SAAS PROD | Deliver education per project plan to business stakeholders to champion latest features and functionality
Enable | SAAS PROD | Host office hours for new users for several weeks in case issues or questions come up
Repeat | SAAS PROD | If rolling out in waves, repeat parallel and enablement for each set of users until everyone is migrated
Cutover | SAAS PROD | Ensure all users are actively on new SaaS instance
Cutover | ALL ON-PREM | Disable legacy environment access
Cutover | ALL ON-PREM | Backup and Shut down legacy servers | [7 empty] | Turn off or decommission servers in order to release resources
Celebrate!
*If you have a Dev instance ordered in SaaS. Also, you may choose to deploy everything to Prod initially if you are migrating at once and not in waves.

## Install Checklist
Sample Activity Checklist - For Illustration Purposes Only - Your upgrade may need more or less activities
Version xx.x on-premise to IBM CA ON CLOUD DEDICATED Version 11.1.X
Note: these steps apply if you still need to prepare content before uploading to the cloud
INSTALL UPGRADE SANDBOX: |  | INSTALL -> CONFIGURE -> TEST
STAGE | ENVIRONMENT | TASK | WHO | COMPLETED Y/N | EST START DATE | EST END DATE | DURATION | ACTUAL START DATE | ACTUAL END DATE | NOTES
Install | upgrade sandbox | Copy installation software to local machines | [7 empty] | Use passport advantage to download supported sofware and copy installation files to local drives for installation
Install | upgrade sandbox | Install upgrade sandbox environment | [7 empty] | Install application software in development
Configure | upgrade sandbox | Configure upgrade sandbox environment | [7 empty] | Use configuration settings from old environment to ensure settings are applied correctly
Configure | upgrade sandbox | copy drivers to the ./drivers folder (CM and data source) | [7 empty] | Install 3rd party drivers and copy required files
Configure | upgrade sandbox | Configure Java based drivers in addition to your ODBC (if you are still using CQM queries) | [7 empty] | You will initially need the ODBC drivers until you convert all of these over. The only exception will be your connection to Powerplay Cubes.
Configure | upgrade sandbox | Check deployment file location | [7 empty] | Confirm access to deployment folder
Configure | upgrade sandbox | confirm you can ping CM, notification, mobile | [7 empty] | Configure access to metadata and configure appropriately
Configure | upgrade sandbox | Check notification (e-mail) | [7 empty] | Configure SMTP server and test
Test | upgrade sandbox | Validate the installation and review the configuration | [7 empty] | Basic functionality test including signon, browsing, and administration
Resolve | upgrade sandbox | Resolve and issues with software configuration and document to apply to future environments | [7 empty] | Troubleshoot issues and record resolution to ensure stability of future installations (UAT and production)
Install | Developer's laptop or CA server | Install & configure & test Appropriate version of FM
Install | Developer's laptop or CA server | Install & configure & test appropriate version of Transformer
Install | Developer's laptop or CA server | Install & configure & test tools like MotioCI / MotioPI / etc
Approve Install

## Upgrade Checklist
Sample Activity Checklist - For Illustration Purposes Only - Your upgrade may need more or less activities
Version xx.x on-premise to IBM CA ON CLOUD DEDICATED Version 11.1.X
Note: these steps apply if you still need to prepare content before uploading to the cloud
Upgrade Content: |  | BACKUP -> UPGRADE -> CONVERT DQM -> VALIDATE -> PROMOTE
STAGE | ENVIRONMENT | TASK | WHO | COMPLETED Y/N | EST START DATE | EST END DATE | DURATION | ACTUAL START DATE | ACTUAL END DATE | Notes
BACKUP | on-premise | Create metadata backup | [7 empty] | Create content export and database copy per database vendor requirments (if database type is changing, content export is required)
BACKUP | on-premise | Identify and backup custom image files (like company logos, custom image files used in reports)
UPGRADE | on-premise upgrade sandbox | Export content to be upgraded from old environment to the upgrade sandbox (or copy the content store database)
UPGRADE | on-premise upgrade sandbox | Import content, upgrade report specifications, and disable automation | [7 empty] | Import content and disable schedules. Upgrade report specifications as an administrative task, not as part of the import to isolate any potential issues
UPGRADE | on-premise upgrade sandbox | Disable automation such as schedules so they do kick off twice (in old environment plus new)
UPGRADE | on-premise upgrade sandbox | Spot Check: Review identified reports, folder structures, access | [7 empty] | Monitor the import and validate imported items like folders, security, capabilities, reports, and models
UPGRADE | on-premise upgrade sandbox | Spot Check: upload a test xls file, create a report, run and schedule to run the report | [7 empty] | this validates functionality, and validates gateway and SSO is properly configured
UPGRADE | on-premise upgrade sandbox | Spot-Check: Pick a few reports and compare | [7 empty] | this indicates you're ready to unleash the QA team and/or tools for validation activities
CONVERT | on-premise upgrade sandbox | Convert any packages based on CQM queries to DQM using the Java drivers installed on the install checklist | [7 empty] | Only exceptions will be for Powerplay Cubes
CONVERT | on-premise upgrade sandbox | If you did not overwrite your published packages for DQM, then re-point reports to the DQM packages
CONVERT | on-premise upgrade sandbox | Open report definitions and choose "accept updated packages" | [7 empty] | If using MotioCI, you may be able to automate this across reports
VALIDATE | on-premise upgrade sandbox | Validate selected content against legacy report and benchmarks | [7 empty] | does it run, does it render the same, what is the impact on the footprint (memory, etc) is it the same as C10
VALIDATE | on-premise upgrade sandbox | Make necessary modifications to reports or models (follow test scripts and remediation plan) | [7 empty] | some remediations will apply across mass reports. There are tools to help with this if you need to make mass updates.
VALIDATE | on-premise upgrade sandbox | Document develoment work to ensure that newly developed packages and reports are tested appropriately
VALIDATE | on-premise upgrade sandbox | Have a few power users check any My Folders content before completing the onpremise validation work
Approve Upgrade Phase Complete

## Compatibility Checklist
Sample Compatible Versions of Software Checklist - for illustration purposes only - you will need to customize this to your needs
Last updated
| Version Cognos 10.x | Version Cognos Analyitcs 11 | Supported by IBM for on-premise upgrade sandbox install?? | Supported by IBM once fully deployed to SaaS? | Example
Operating System
Server |  |  |  |  | RHEL 7.5
Client |  |  |  |  | Windows 10
Mobile client |  |  |  |  | iOS 12.1.2
Virtualization \ Hypervisor Technology
On Premise Server (VMWare \ Hyper-V \ KVM \ XenServer) |  |  |  |  | VMWare ESXi 6.5
Cloud platform Server (AWS \ Azure \ SoftLayer) |  |  |  |  | SoftLayer CloudLayer Services
Runtime Environment
Server Java version (if not using bundled JRE included in Windows install) |  |  |  |  | IBM JRE 8.0.1
Application Server
Server (websphere \ tomcat \ weblogic) |  | embedded WebSphere Application Server |  |  | embedded WebSphere Application Server
Archive Server
Report Archive Facility |  |  |  |  | FileNet Content Manager 5.2
Collaboration
Task and Notification Server |  |  |  |  | IBM Connections 5.0
Content Server
Enterprise Conent Store Server (Db2 \ SQL \ Oracle) |  |  |  |  | Db2 Enterprise Server 11.1.0
Content Viewers
Client Reader |  |  |  |  | Adobe Reader XI
Client Productivity |  |  |  |  | Microsoft Office 2016
Data Dictionary
Companion server for metadata |  |  |  |  | Infosphere Information Server 11.5
Data Sources
Data provider 1 |  |  |  |  | Db2 Enterprise Server 10.5
Data provider 2 |  |  |  |  | Cognos TM1 10.2.2
Data provider 3 |  |  |  |  | IBM Planning Analytics Local 2.0.5
Data provider 4
Data provider 5
Data provider 6
Software Development Tools
SDK support software (JRE \ .NET) |  |  |  |  | IBM JRE 7.0
Authentication \ Identity Management
Authentication Provider |  |  |  |  | Microsoft Active Directory 2016
Web Browser
Client Browser |  |  |  |  | Microsoft Internet Explorer 11
Mobile Client Browser |  |  |  |  | Apple Safari 11.1
Web Server
Server Software hosting additional gateway installation |  |  |  |  | IBM HTTP Server 9.0